## Sprint Backlog
Project: Development for Real-Time Competitor Strategy Tracker for E-commerce ¦ Duration: 2 months ¦ Team Member: Solo (Intern)
US ID | Task ID | Task Description | Team Member
1 | 1 | Identify competitor websites and data points | Solo (Intern)
1 | 2 | Develop web scraper to collect competitor data | Solo (Intern)
1 | 3 | Store scraped data in structured format (CSV/DB) | Solo (Intern)
2 | 1 | Clean and preprocess collected data | Solo (Intern)
2 | 2 | Automate daily scraping | Solo (Intern)
2 | 3 | Create data visualization samples (price trends) | Solo (Intern)
3 | 1 | Develop ML model for strategy/price prediction | Solo (Intern)
3 | 2 | Analyze competitor trends | Solo (Intern)
3 | 3 | Integrate model output with dashboard | Solo (Intern)
4 | 1 | Build Streamlit dashboard | Solo (Intern)
4 | 2 | Add email alert system for major changes | Solo (Intern)
4 | 3 | Final testing and documentation | Solo (Intern)